## One Page Project Manager
Key Stakeholders
Id | Task Name | Owner | Start Date | End Date | Actual | Forecast | Duration | Status | Milestones and Key Dates
1 | Analysis | Neel | 2015-01-02 | 2015-01-08 | 100 | 100 | 4 | 0 | 1
2 | Testing | Kam | 2015-08-21 | 2015-08-25 | 100 | 100 | 3 | 0 | 2
3 | Build | Kam | 2015-08-25 | 2015-08-28 | 100 | 100 | 4 | 0 | 3
4 | QAT | Zam | 2015-08-15 | 2015-09-10 | 100 | 100 | 19 | 0 | 4
5 | Performance Anlaysis | Sjum | 2015-09-03 | 2015-09-28 | 100 | 100 | 17 | 0 | 5
6 | Team Reporting | Sum | 2015-08-03 | 2015-08-05 | 59 | 100 | 3 | 41 | Task Meter
7 | Generate Documentation | Kum | 2015-08-22 | 2015-08-24 | 50 | 100 | 2 | 50
8 | Code Review | Zam | 2015-08-22 | 2015-08-26 | 61 | 100 | 4 | 39
9 | Test Analysis | Neel | 2015-09-05 | 2015-09-11 | 0 | 100 | 5 | 100
10 | Test Analysis | Neel | 2015-10-05 | 2015-10-23 | 12 | 100 | 15 | 88
11 | Execute | Neel | 2015-10-06 | 2015-10-27 | 13 | 100 | 16 | 87
12
13
14
15
16
17 | [8 empty] | Resource Work Load (days)
18
19
20
21
22
Top 5 Risks & Issues
1
2
3
4 | [8 empty] | Notes & To Do List
5 | [8 empty] | 1 | Submit papers | 2015-02-12
Open Actions and Change Requests | [8 empty] | 2 | Call helpdesk for Support ticket on Server H/W. | 2015-10-12
1 | [8 empty] | 3 | Check system requirements | 2015-11-12
2 | [8 empty] | 4 | Update Sponsor on budget changes | 2015-12-11
3 | [8 empty] | 5
4 | [8 empty] | 6
5 | [8 empty] | 7
Template created by www.techno-pm.com
Formulas:
End Date = WORKDAY([Start Date],[Duration]-1,Data!$K2:K18)
Forecast = IF([Start Date]>TODAY(),0,IF(TODAY()>=[End Date],"100",IF([End Date]>TODAY(),(100*NETWORKDAYS([Start Date],TODAY()))/[Duration],"")))

## Data
Not Started | 1 | Sl NO | Resources | Workload | Sl. No | Public Holidays | Date
On Track | 5 | 1 | Neel | 40 | 1 | Test | 2015-01-07
Concern | 0 | 2 | Kam | 7 | 5 | Test | 2015-09-07
Delayed | 6 | 3 | Zam | 23 | 6
Total Tasks | 11 | 4 | Sum | 3 | 7
|  | 5 | Sjum | 17 | 8
|  | 6 | Kum | 2 | 9
|  | 7 | Rum | 0 | 10
11
12
13
14
15
16
17
18
19
20