## Sheet1
PRODUCT BACKLOG EXAMPLE
ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
1 | Administrator | see a list of all members and visitors | I can monitor site visits | Must | 1 | Done
2 | Administrator | add new categories | I can allow members to create engaging content | Must | 1 | Done
3 | Administrator | add new security groups | security levels are appropriate | Must | 1 | Done
4 | Administrator | add new keywords | content is easy to group and search for | Must | 1 | Done
5 | Administrator | delete comments | offensive content is removed | Must | 1 | Done
6 | Administrator | block entries | competitors and offenders cannot submit content | Must | 1 | Done
7 | Administrator | change site branding | the site is future-proofed in case brand changes | Could | 1 | Done
8 | Member | change my password | I can keep secure | Must | 1 | Done
9 | Member | update my contact details | I can be contacted by Administrators | Must | 2 | Work in Progress
10 | Member | update my email preferences | I'm not bombarded with junk email | Should | 2 | Work in Progress
11 | Member | share content to social networks | I can promote what I find interesting | Could | 2 | Work in Progress
12 | Visitor | create an account | I can benefit from member discounts | Must |  | To be started
13 | Visitor | login | I can post new entries | Must |  | To be started
14 | Visitor | add comments | I can have a say | Must |  | To be started
15 | Visitor | suggest improvements | I can contribute to the site usability | Should |  | To be started
16 | Visitor | contact the Administrators | I can directly submit a query | Could |  | To be started
17 | Visitor | follow a member's updates | I'm informed of updates from members I find interesting | Should |  | To be started
18 | Visitor | view a member's profile | I can know more about a member | Must |  | To be started
19 | Administrator | generate incoming traffic report | I can understand where traffic is coming from | Must |  | To be started
20 | Administrator | export incoming traffic report into .pdf | I can share traffic data with my leadership team | Must |  | To be started