## Plan
Action Plan |  | Fix Memory Leak Issues in Test Servers. |  | Description |  | Due to the recent software upgrade some of the test servers are having an issue of memory leak and often stop responding during integration testing. |  |  |  | Date & Champion |  | 12-Jan-2016 Swapnil Wale
Goals | [5 empty] | Action Plan Timeline
Goal # 1 | Identify the root cause of the issue by analyzing all the clusters. |  |  |  |  | Task | Start | Finish | Progress | Status | Comments
[6 empty] | Analyze server settings and issue messages | 2017-01-12 | 2017-01-15 | 95% | On Track
Goal # 2 | Present the findings to CCB (Change Control Board). |  |  |  |  | Share messages with vendor | 2017-01-16 | 2017-01-19 | 67% | Worry
[6 empty] | Code and Build Fix | 2017-01-20 | 2017-01-25 | 53% | Bad | Delayed due to environment issues.
Goal # 3 | Test and develop a break-fix patch with the fix. |  |  |  |  | Test in SIT | 2017-01-26 | 2017-01-28 | 0%
[6 empty] | Deploy Fix | 2017-01-29 | 2017-01-29 | 0%
Goal # 4 | Run performance tests on servers to ensure the fix has worked. |  |  |  |  | Performance Test | 2017-02-02 | 2017-02-02 | 0%
Impact Assessment |  |  |  | Risks |  |  |  | Resources & Dependencies
Business |  |  | High | Risk # 1 | The initial step might reveal a much more complex problem which could mean the timeline expands. |  |  | Req # 1 | ABAP developer needed for two weeks. |  |  |  | Yes
Customer |  |  | Medium
Brand |  |  | Low | Risk # 2 | The resources allocated to the task are not full time so may not be full effective if they break their analysis into parts. |  |  | Req # 2 | The plan is dependent on projects finishing on time/ if the project gets delayed then the plan will need to be revised. |  |  |  | No
Financial |  |  | Low
Data |  |  | Medium | Risk # 3 | The fix might need complex change to the architecture which might need more resources. |  |  | Req #3 | QA resource required to do performance testing. |  |  |  | No
Technology |  |  | High
Compliance |  |  | High |  |  |  |  | Req #4 | Will need additional licenses for the dev tools.
Overall Assessment |  |  | Low