## Sheet1
Program Tracker | [15 empty] | 1
0
| Program Name: | Advance APP Development |  |  |  |  | Updated On : | 2020-10-08
| Program Manager Name: | John Fendi
|  |  | Dept |  | Expected | Months | Yes/No | Manual Update | Status | Yes/no |  | Months | Estimated | Actual
# | Project Tittle | Responsible Person | Process Area | Start Date | End Date | Duration | Charted ? | %Progress | Phase | Closed? | Finish date | Delayed | Gain in $ | Gain in $ | Gain VAR
1 | Submitting the test Summary Report | Ron | Testing | 2020-09-14 | 2021-01-28 | 4.5333 | 1 | 5% | Analyse | No | 2022-03-02 |  | 320000 | 0 | -320000
2 | Present the Cutover plan for approval | Anamaria | Developer | 2020-09-17 | 2021-01-21 | 4.2 | 1 | 10% | Approved | No | 2022-03-02 |  | 11900 | 12900 | 1000
3 | Version 20.4 released for E2E (End to End) testing | Mary | Developer | 2020-09-22 | 2021-02-24 | 5.1667 | 0 | 100% | Completed | Yes | 2021-03-12 | 0.53333 | 32775 | 30000 | -2775
4 | E2E testing | Sarah | Testing | 2020-09-30 | 2021-02-27 | 5 | 0 | 30% | Control | No | 2021-03-02 |  | 205000 | 0 | -205000
5 | Beta testing start | Sam | Testing | 2020-10-02 | 2021-04-02 | 6.0667 | 1 | 25% | Measure | No | 2021-03-02 |  | 112200 | 0 | -112200
6 | Cutover Finish | John | Developer | 2020-10-06 | 2021-04-13 | 6.3 | 0 | 50% | Completed | Yes | 2021-02-26 | -1.5333 | 52000 | 0 | -52000
7 | Go-Live | George | Developer | 2021-04-20 | 2021-05-20 | 1 | 1 | 0% | Analyse | No | 2021-02-27 |  | 274000 | 0 | -274000
8 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-21 | 2021-05-21 | 1 | 0 | 0% | Approved | Yes | 2021-02-28 | -2.7333 | 0 | 0 | 0
9 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-22 | 2021-05-22 | 1 | 0 | 0% | Measure | No | 2021-03-01 |  | 0 | 0 | 0
10 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-23 | 2021-05-23 | 1 | 1 | 0% | Control | Yes | 2021-03-02 | -2.7333 | 0 | 0 | 0
11 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-24 | 2021-05-24 | 1 | 1 | 0% | Analyse | No | 2021-03-03 |  | 0 | 0 | 0
12 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-25 | 2021-05-25 | 1 | 1 | 0% | Completed | No | 2021-03-04 |  | 0 | 0 | 0
13 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-26 | 2021-05-26 | 1 | 0 | 0% | Cancelled | Yes | 2021-03-05 | -2.7333 | 0 | 0 | 0
14 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-27 | 2021-05-27 | 1 | 1 | 0% | Measure | No | 2021-03-06 |  | 0 | 0 | 0
15 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-28 | 2021-05-28 | 1 | 1 | 0% | Analyse | Yes | 2021-03-07 | -2.7333 | 0 | 0 | 0
16 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-29 | 2021-05-29 | 1 | 1 | 0% | Approved | No | 2021-03-08 |  | 0 | 0 | 0
17 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-04-30 | 2021-05-30 | 1 | 0 | 0% | Control | Yes | 2021-03-09 | -2.7333 | 0 | 0 | 0
18 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-01 | 2021-05-31 | 1 | 1 | 0% | Completed | No | 2021-03-10 |  | 0 | 0 | 0
19 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-02 | 2021-06-01 | 1 | 1 | 0% | Completed | No | 2021-03-11 |  | 0 | 0 | 0
20 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-03 | 2021-06-02 | 1 | 1 | 0% | Approved | Yes | 2021-03-12 | -2.7333 | 0 | 0 | 0
21 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-04 | 2021-06-03 | 1 | 0 | 0% | Measure | No | 2021-03-13 |  | 0 | 0 | 0
22 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-05 | 2021-06-04 | 1 | 1 | 0% | Control | Yes | 2021-03-14 |  | 0 | 0 | 0
23 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-06 | 2021-06-05 | 1 | 1 | 0% | Analyse | No | 2021-03-15 |  | 0 | 0 | 0
24 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-07 | 2021-06-06 | 1 | 1 | 0% | Completed | Yes | 2021-03-16 |  | 0 | 0 | 0
25 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-08 | 2021-06-07 | 1 | 0 | 0% | Cancelled | No | 2021-03-17 |  | 0 | 0 | 0
26 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-09 | 2021-06-08 | 1 | 1 | 0% | Completed | No | 2021-03-18 |  | 0 | 0 | 0
27 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-10 | 2021-06-09 | 1 | 1 | 0% | Approved | Yes | 2021-03-19 |  | 0 | 0 | 0
28 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-11 | 2021-06-10 | 1 | 1 | 0% | Measure | No | 2021-03-20 |  | 0 | 0 | 0
29 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-12 | 2021-06-11 | 1 | 0 | 0% | Control | Yes | 2021-03-21 |  | 0 | 0 | 0
30 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-13 | 2021-06-12 | 1 | 1 | 0% | Analyse | No | 2021-03-22 |  | 0 | 0 | 0
31 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-14 | 2021-06-13 | 1 | 1 | 0% | Completed | Yes | 2021-03-23 |  | 0 | 0 | 0
32 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-15 | 2021-06-14 | 1 | 1 | 0% | Cancelled | No | 2021-03-24 |  | 0 | 0 | 0
33 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-16 | 2021-06-15 | 1 | 0 | 0% | Completed | No | 2021-03-25 |  | 0 | 0 | 0
34 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-17 | 2021-06-16 | 1 | 1 | 0% | Approved | Yes | 2021-03-26 |  | 0 | 0 | 0
35 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-18 | 2021-06-17 | 1 | 1 | 0% | Measure | No | 2021-03-27 |  | 0 | 0 | 0
36 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-19 | 2021-06-18 | 1 | 1 | 0% | Control | Yes | 2021-03-28 |  | 0 | 0 | 0
37 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-20 | 2021-06-19 | 1 | 0 | 0% | Analyse | No | 2021-03-29 |  | 0 | 0 | 0
38 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-21 | 2021-06-20 | 1 | 1 | 0% | Completed | Yes | 2021-03-30 |  | 0 | 0 | 0
39 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-22 | 2021-06-21 | 1 | 1 | 0% | Cancelled | No | 2021-03-31 |  | 0 | 0 | 0
40 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-23 | 2021-06-22 | 1 | 1 | 0% | Measure | No | 2021-04-01 |  | 0 | 0 | 0
41 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-24 | 2021-06-23 | 1 | 0 | 0% | Control | Yes | 2021-04-02 |  | 0 | 0 | 0
42 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-25 | 2021-06-24 | 1 | 1 | 0% | Analyse | No | 2021-04-03 |  | 0 | 0 | 0
43 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-26 | 2021-06-25 | 1 | 1 | 0% | Completed | Yes | 2021-04-04 |  | 0 | 0 | 0
44 | Lorem ipsum dolor sit amet | Lorem Ipsum | Type here | 2021-05-27 | 2021-06-26 | 1 | 1 | 0% | Cancelled | No | 2021-04-05 |  | 0 | 0 | 0

## Sheet2
Project