## Basic
SAP Preparation Project
Updated on 19-Dec-2017
Task | Aggregate Hours | Actual Hours
|  | Day 5 | Day 4 | Day 3 | Day 2 | Day 1 | Status | Comments
Peer review - Blueprint | 10 | 3 | 5 | 0 | 1 | 1 | On Track
Internal presentation of the blueprint | 6 | 1 | 3 | 0 | 2 | 0 | On Track
Submit the Blueprint to the client | 2 | 0.5 | 1 | 0 | 0.5 | 0 | On Track
Build the detailed plan | 8 | 2 | 1.5 | 0 | 3 | 1.5 | On Track
Allocate resources to the plan | 6 | 1 | 3 | 0 | 1 | 1 | On Track
Analyse the discrepancies between the plan and the available resources | 4 | 1 | 1 | 0 | 1 | 1 | On Track
Put together the recruitment plan | 6 | 0.5 | 1 | 0 | 2 | 2.5 | On Track
Recruit additional employees | 3 | 1.5 | 0 | 0 | 1.5 | 0 | On Track | Additional hour was required to send the updated requirements to the 3rd party recruiters
Baseline Hours | 45 | 36 | 27 | 18 | 9 | 0 |  | The plan was to work 9 hours each day for 5 days
Actual Hours | 45 | 34.5 | 19 | 19 | 7 | 0
Commentary: At the end of Day 5 the project was ahead of the plan (the green line is below the dashed orange line) At the end of Day 2 it was behind the plan (the green line is above the dashed orange line) From Day 1 and onwwards it is ahead of the plan