## Project Plan
No. | Task Details | Owner | Start | Finish | Progress | Status | Risks/Issues | Comments
1 | Project Initiation
1.1 | Business Case | Ted | 2016-02-12 | 2016-02-15 | 100% | Complete
1.2 | Funding Approval | Ted | 2016-02-15 | 2016-02-18 | 90% | Complete |  | Funding approved.
1.3 | Resource Planning | Ted | 2016-02-19 | 2016-02-24 | 100% | Complete
1.4 | Schedule Planning | Ted | 2016-02-25 | 2016-02-27 | 100% | Complete
1.5 | Arrange Kick off Meeting | Ted | 2016-03-01 | 2016-03-05 | 100% | Complete |  | Some concerns raised about the scope
2 | Analysis
2.1 | Business Requirement Specification | Zuber | 2016-03-05 | 2016-03-10 | 65% | Concern | Delay in business input. | Reminder sent to SME.
2.2 | Functional Requirement Specification | Zuber | 2016-03-10 | 2016-03-15 | 90% | On Track
2.3 | Technical Requirement Specification | Zuber | 2016-03-15 | 2016-03-20 | 45% | On Track
2.4 | Requirement Walkthrough | Zuber | 2016-03-20 | 2016-03-23 | 25% | On Track
2.5 | Requirements Sign Off | Zuber | 2016-03-23 | 2016-03-25 | 35% | Concern | Last minute changes. | Can delay the entire project.
3 | Design
3.1 | High Level Design | Jo | 2016-03-25 | 2016-03-27 | 5% | Delayed | Unplanned leaves.
3.2 | Detailed Design | Jo | 2016-03-27 | 2016-03-28 |  | Pending
3.3 | Design Walkthrough | Jo | 2016-04-01 | 2016-04-05 |  | Pending
3.4 | Design Sign Off | Jo | 2016-04-05 | 2016-04-10 |  | Pending
4 | Development
4.1 | Build Component 1 | Sean | 2016-04-11 | 2016-04-19 |  | Pending
4.2 | Unit Testing Component 1 | Sean | 2016-04-20 | 2016-04-24 |  | Pending
4.3 | Build Component 2 | Zac | 2016-04-11 | 2016-04-19 |  | Pending
4.4 | Unit Testing Component 2 | Zac | 2016-04-20 | 2016-04-24 |  | Pending
4.5 | Integration Testing | Sean/Zac | 2016-04-25 | 2016-04-28 |  | Pending
5 | Testing
5.1 | Create Test Plan | Zen/Sam | 2016-04-28 | 2016-05-05 |  | Pending
5.2 | Create Test Cases | Zen/Sam | 2016-05-10 | 2016-05-15 |  | Pending
5.3 | Execute Test Case Round - 1 | Zen/Sam | 2016-05-16 | 2016-05-25 |  | Pending
5.4 | Record Defects Round - 1 | Zen/Sam | 2016-05-25 | 2016-06-01 |  | Pending
5.5 | Fix Defects | Sean/Zac | 2016-06-02 | 2016-06-05 |  | Pending
5.6 | Execute Test Case Round - 2 | Zen/Sam | 2016-06-10 | 2016-06-15 |  | Pending
5.7 | Record Defects Round - 2 | Zen/Sam | 2016-06-16 | 2016-06-18 |  | Pending
5.8 | Draft Testing Report | Zen/Sam | 2016-06-19 | 2016-06-20 |  | Pending
6 | User Acceptance
6.1 | Draft UAT Test Cases | Ram | 2016-06-21 | 2016-06-25 |  | Pending
6.2 | Perform UAT - Round 1 | Ram | 2016-06-25 | 2016-06-30 |  | Pending
6.3 | Record Defects | Zuber | 2016-07-01 | 2016-07-05 |  | Pending
6.4 | Fix Defects | Sean/Zac | 2016-07-10 | 2016-07-15 |  | Pending
6.5 | Perform UAT - Round 2 | Ram | 2016-07-16 | 2016-07-20 |  | Pending
7 | Deploy
7.1 | Draft deployment plan | Kam | 2016-07-25 | 2016-07-27 |  | Pending
7.2 | Dry Run deployment | Kam | 2016-07-28 | 2016-07-29 |  | Pending
7.3 | Fix Dry Run Observations | Kam | 2016-07-29 | 2016-07-29 |  | Pending
7.4 | Implement Production | Kam | 2016-08-01 | 2016-08-02 |  | Pending
8 | Go Live |  | 2016-08-03 | 2016-08-03
Formulas:
Start = [Finish, row above]