## Template 1
# | Task | PM | COO | PMO | Admin | Status
1 | Define functional requirements | I | A, I |  |  | Done
2 | Plan the deployment of the system | A, I |  | R | I | In Process
3 | Test the system | I | C, I | I | I | In Process
4 | Track the testing status | I | A | R | C | Not Started
5 | Present the status to the customer | A | R | C | C | Cancelled
6 | Migrate data from the legacy systems | I | A | I |  | Not Started
7 | Cutover from legacy to new system | A | R | I |  | Not Started
8 | Manage Go Live Issues | A | A |  | R | Not Started
9 | Project Closure Workshop | R | I | I | I | Not Started
10 | Project Closure Document | R | C | A | C | Not Started
11 | Approve Project Closure Document | R | R | A | C | Not Started
Legend
R | Responsible
A | Accountable
C | Consulted
I | Informed

## Template 2
# | Task | Supply Chain VP | Sourcing Expert | PMO | Sourcing TL | Materials Planner | Logistics | Due Date | Status
1 | Receive the requirements | I | R | I | A |  |  | 2017-06-02 | Done
2 | Plan the process | A | C, I | R | C, I | C |  | 2017-06-03 | In Process
3 | Send the RFP to vendors | I | R | I | A |  |  | 2017-06-07 | In Process
4 | Agree on the best offer | C, I | R |  | A | I | I | 2017-06-14 | In Process
5 | Sign the contract | A | I | I | R | I | I | 2017-06-15 | In Process
6 | Track the progress | I | C | I | A | I | R | 2017-07-03 | Not Started
7 | Deliver the goods / service | A | I | I | R | I | I | 2017-07-09 | Not Started
This example is of a sourcing process
Legend
R | Responsible
A | Accountable
C | Consulted
I | Informed