## Sprint
| Project Manager | Einat Horowitz | Update Date |  | 2017-12-18
| Project | Group Sharing App | Updated By |  | Pradeep Singh
Sprints |  |  | Aggregate Aprints | Baseline Sprint Completion |  |  | Actual Sprint Completion |  |  | Comments
Number | Feature | Purpose |  | Week #3 | Week #2 | Week #1 | Week #3 | Week #2 | Week #1
1.1 | Inviting a friend | Allows the user to invite friends to a group discussion |  | 1 |  |  | 1
1.2 | Liking a post | Allows the users to click on a "like" button |  | 1 |  |  | 1
2.1 | Adding a video link | Upload a link to a video on any video sharing site |  |  | 1 |  |  |  | 1 | This feature proved to be harder than anticipated,a dnrequired buying help from an SME
3.1 | Deleting a sent message | The users can delete a sent message |  | 1 |  |  |  | 1 |  | Opern source allowed to complete earlier than planned
3.2 | Statistics on sent messages (number of people read, number of likes) | Allows the user to see how many messages they sent, how many people liked each one |  |  | 1 |  |  | 1
3.3 | Emoji customization | The users can change the appearance of the emoji's |  |  |  | 1 |  |  | 1
3.4 | Picture uploading | Allows the users to upload a picture to the group forum |  |  |  | 1 |  |  | 1
4.1 | Location sender | allows sharing the location with the group |  |  | 1 |  |  | 1
4.2 | Remove from group | The owner of a group can remove any of the members |  |  |  | 1 |  |  | 1
Sprint Completion Week Baseline |  |  | 9 | 6 | 3 | 0
Actual Sprint Completion Week |  |  | 9 |  |  |  | 7 | 4 | 0
Commentary: The sprints started off later than planned (1 sprint later than planned for week #3 and week #2), but on the third and final week the team was able to complete on schedule