## Decision Log
No. | Decision Details | Impact | Proposed Date | Proposed By | Status | Approved By | Date | Resulting Action/Comments
1 | Increase the scope of the project to include UI testing. The initial scope of the project did not include UI Testing. | The project go live will be delayed by 3 weeks. | 2015-07-26 | Team | Approved | Manager | 2015-09-30 | The project plan will be changed to include additional effort of 3 weeks. Action item assigned to project manager.
2 | Additional requirements added to the project scope. Change Request #002. | No material impact on the project delivary date. | 2015-03-23 | SME | Approved | Project Control | 2015-09-30 | Approved as no material impact.
3 | Logo design cost of $5,000 not included in the initial budget. The logo design is needed as a standard. | The project cost will go up by $5,000. | 2015-06-25 | Marketing | Pending |  |  | Waiting Approval
4 | The HR Module from the application will be descoped as the business requirements are not finalized. | The HR team will have to use the legacy system. A separate project will need to be initiated to build the HR System. | 2015-06-24 | Project Manager | Abandon |  |  | Abandoned as not needed.
5 | Add additional resources to bring in the project go live date. 3 developers and one tester will be needed to get the go live date to 3rd Sep. | Resources will need to be contracted which will cost the project additional $45,000. | 2015-08-25 | Team | Declined |  | 2015-08-27 | The decision recommendation was declined as no additional funding is available.

## Config
Status | Approvers
Approved | Manager
Pending | Project Control
Declined | Project Manager
Abandon