## Release
Project Name |  | Physical App updates |  |  |  | Updated On |  | 2017-12-19
Updated by |  | Gary Walsh
Features |  |  | Actual Points |  |  |  |  | Comments
Number | Name | Points | Sprint #5 | Sprint #4 | Sprint #3 | Sprint #2 | Sprint #1
1 | Allow GPS to track the movements of the users | 25 | 0 | 10 | 10 | 5 | 0
2 | Collect data regarding ascent / descent and number of KM's walked | 32 | 0 | 14 | 8 | 5 | 5
3 | Present the route walked in a graphical map | 15 | 0 | 0 | 0 | 0 | 15 | Took longer than planned, due to GPS connectivity issues
4 | Allow different maps backgrounds | 20 | 10 | 0 | 0 | 0 | 10 | Loading maps diminished response times, solution took a while
5 | Compare similar routes | 10 | 0 | 0 | 0 | 5 | 5
6 | Allow route planning | 35 | 25 | 0 | 0 | 0 | 10
7 | Present real time plan vs. actual statistics | 20 | 5 | 5 | 5 | 0 | 5
8 | Add pop-ups | 40 | 10 | 10 | 15 | 5 | 0
9 | Sharing maps and routes with other users | 15 | 0 | 0 | 10 | 0 | 5
10 | Allow exporting of maps to .GPX files | 20 | 5 | 5 | 5 | 0 | 5
Baseline Points |  | 232 | 185.6 | 139.2 | 92.8 | 46.4 | 0 | The baseline point use per sprint is linear
Actual Points |  | 232 | 177 | 133 | 80 | 60 | 0
Commentary: For the first 4 sprints, the actual was ahead of plan, and at the beginning of the 5th sprint it was behind schedule. At the end of the 5th and final sprint the team was able to overcome the lag and complete the features on schedule