## SW
Task Name | Priority | Owner | Start Date | End Date | Status | Comments
Sprint #1 - Requirement Mapping
Map out the features required | High | Amit Malik | 2017-11-30 | 2017-12-05 | In Process | The overall picture
Map out the expected users and requirements | Medium | Helmut Drabe | 2017-11-30 | 2017-12-04 | In Process | Each group of users will have different permissions
Map the reports required | Low | Shirin Sandra | 2017-12-04 | 2017-12-08 | Not Started
Sprint #2 - Feature Designing
Design the interface features | High | Franny Sheldom | 2017-12-05 | 2017-12-12 | Not Started
Design the printing features | Low | Leonard Beaty | 2017-11-30 | 2017-12-01 | Cancelled | No printing will be required - paperless office
Define the response times | Medium | Leonard Beaty | 2017-11-30 | 2017-12-01 | In Process
Design the reports, dashboards and charts features | High | Don A. Chaney | 2017-12-11 | 2017-12-14 | Not Started
Design the AI (Artificial Intelligence) features | Medium | Leonard Beaty | 2017-12-07 | 2017-12-11 | Not Started
Sprint #3 - Code Writing
Write the code for the interface | High | Peggy Walters | 2017-11-28 | 2017-11-30 | Done | 2 variants were re-tested (initially failed)
Write the code for the reports , dashboards and charts | Medium | Peggy Walters | 2017-11-30 | 2017-12-01 | In Process | So far all is well
Write the code for AI features | High | Anand Das | 2017-12-05 | 2017-12-11 | Not Started
Sprint #4 - QA
Test the interface | Medium | Meir Greizman | 2017-12-01 | 2017-12-08 | In Process
Test the reports, dashboards and charts | Medium | Ronald McQueen | 2017-12-05 | 2017-12-11 | Not Started
Test the AI features | Medium | Ronald McQueen | 2017-12-12 | 2017-12-15 | Not Started
Test the response times | High | Meir Greizman | 2017-12-05 | 2017-12-12 | Not Started
Sprint #5 - User Testing
Define the testing parameters | Medium | Christian Schmidt | 2017-12-05 | 2017-12-11 | Not Started | For the Beta testers
Collect the initial results | Low | Christian Schmidt | 2017-12-07 | 2017-12-12 | Not Started | No analysis required, just to see that it is on track
Collect the final results | Medium | Meir Greizman | 2017-12-12 | 2017-12-13 | Not Started
Analyse the results and recommend fixes and new features for the next version | High | Norris Coleman | 2017-12-18 | 2017-12-22 | Not Started