## Product
Product: | Pain Killer Pill |  | Updated on | 2017-12-20
Owner: | Roy O'Bannon |  | Scrum Master: | Olivia Taine
Product |  |  | Actual Points |  |  |  | Comments
WBS | Name | Points | 4th Story | 3rd Story | 2nd Story | 1st Story
1.1 | Conduct initial patient screening | 12 | 10 | 2 | 0 | 0
1.2 | Set test parameters | 20 | 10 | 10 | 0 | 0
1.3 | Approve parameters | 5 | 0 | 5 | 0 | 0
2.1 | Conduct patient testing | 10 | 0 | 8 | 2 | 0
2.1.1 | Collate results from different groups | 25 | 0 | 5 | 5 | 15
2.1.2 | Analyse results | 35 | 0 | 10 | 10 | 15
2.1.3 | Present results vs. parameters | 15 | 0 | 0 | 7 | 8
3.1 | Set clinical trial parameters | 10 | 0 | 10 | 0 | 0
3.2 | Compare parameters with FDS regulations | 12 | 0 | 0 | 10 | 2
4 | Publish findings in peer magazines | 5 | 0 | 0 | 0 | 5
5.1 | Receive feedback | 5 | 0 | 0 | 0 | 5
5.2 | Corrections following feedback | 20 | 0 | 0 | 0 | 0 | Feature dropped since the approval was received prior to the feedback
Baseline Points |  | 174 | 130.5 | 87 | 43.5 | 0
Actual Points |  | 154 | 134 | 84 | 50 | -20
Commentary: The last feature was dropped from the product, thus leaving a 20 point gap at the end of the 1st story