## Plan
# | Task Name | Resource | Duration (d) | Start | Finish | % Complete | Comments
1 | User Stories
1 | Identify Key stakeholders | Business Analyst | 5 | 2016-09-04 | 2016-09-09
1.2 | Form project team | Project Manager | 15 | 2016-09-10 | 2016-09-30
1.3 | User Story workshops - 1 | Business Analyst | 10 | 2016-10-01 | 2016-10-14
1.4 | User Story workshops - 2 | Business Analyst | 10 | 2016-10-15 | 2016-10-28
1.5 | User Stories Walk-through and sign off | Business Analyst | 10 | 2016-10-29 | 2016-11-11
2 | Product Backlog
2.1 | Create Product Backlog | Project Manager | 5 | 2016-11-12 | 2016-11-18
2.2 | Story Estimation | Project Team | 5 | 2016-11-19 | 2016-11-25
2.3 | Prioritize | Project Manager | 5 | 2016-11-26 | 2016-12-02
3 | High Level Sprint Planning
3.1 | Create project timeline | Project Manager | 5 | 2016-12-03 | 2016-12-09
3.2 | Draft resource plan | Project Manager | 5 | 2016-12-10 | 2016-12-16
3.3 | Plan project budget | Project Manager | 5 | 2016-12-17 | 2016-12-23
4 | Sprint - 1
4.1 | Sprint 1 - Planning | Project Team | 10 | 2016-12-24 | 2017-01-06
4.2 | Sprint 1 - Execution | Project Team | 10 | 2017-01-07 | 2017-01-20
4.3 | Sprint 1 - Demo | Project Team | 10 | 2017-01-21 | 2017-02-03
4.4 | Sprint 1 - Implementation | Project Team | 10 | 2017-02-04 | 2017-02-17
4.5 | Sprint 1 - Retrospective | Project Team | 10 | 2017-02-18 | 2017-03-03
5 | Sprint - 2
5.1 | Sprint 2 - Planning | Project Team | 10 | 2017-03-04 | 2017-03-17
5.2 | Sprint 2 - Execution | Project Team | 10 | 2017-03-18 | 2017-03-31
5.3 | Sprint 2 - Demo | Project Team | 10 | 2017-04-01 | 2017-04-14
5.4 | Sprint 1 - Implementation | Project Team | 10 | 2017-04-15 | 2017-04-28
5.4 | Sprint 2 - Retrospective | Project Team | 10 | 2017-04-29 | 2017-05-12
6 | Sprint - 3
6.1 | Sprint 3 - Planning | Project Team | 10 | 2017-05-13 | 2017-05-26
6.2 | Sprint 3 - Execution | Project Team | 10 | 2017-05-27 | 2017-06-09
6.3 | Sprint 3 - Demo | Project Team | 10 | 2017-06-10 | 2017-06-23
6.4 | Sprint 1 - Implementation | Project Team | 10 | 2017-06-24 | 2017-07-07
6.5 | Sprint 3 - Retrospective | Project Team | 10 | 2017-07-08 | 2017-07-21
7 | Project Close
7.1 | Conduct Project Review | Project Manager | 10 | 2017-07-22 | 2017-08-04
7.2 | Publish Project Lesson Learnt Report | Project Manager | 10 | 2017-08-05 | 2017-08-18
Formulas:
Finish = WORKDAY([Start],[Duration (d)])
Start = [Finish, row above]+1