## Dashboard
Backlog | [5 empty] | Active
# | Description | Status | Sprint - 1 | Start | 2016-10-30 | Sprint - 2 | Start | 2016-11-12 | Sprint - 3 | Start | 2016-11-15 | Sprint - 4 | Start | 2016-12-26
1 | Website Design | Sprint - 1 |  | Finish | 2016-11-10 |  | Finish | 2016-11-18 |  | Finish | 2016-12-23 |  | Finish | 2016-11-15
2 | Homepage Design | Sprint - 1 | Scope |  |  | Scope |  |  | Scope |  |  | Scope
3 | Login Page Design | Sprint - 1 | Website Design |  | Complete | Build backup module |  | Complete | Dev Accounts Page |  |  | Integration testing phase 1
4 | Design Account Page | Sprint - 1 | Homepage Design |  | Complete | Dev login service |  | Complete | Test Accounts Page |  |  | Integration testing phase 2
5 | Build backup module | Sprint - 2 | Login Page Design |  | Complete | Dev Homepage design |  | Delayed | Test backup module
6 | Dev login service | Sprint - 2 | Design Accounts Page |  | Complete | Test Homepage |  | On Track | Build reporting module
7 | Dev Homepage design | Sprint - 2 |  |  |  | Test Login Service |  | Behind | Test reporting module
8 | Test Homepage | Sprint - 2 | Burndown Chart |  |  | Burndown Chart |  |  | Burndown Chart |  |  | Burndown Chart
9 | Test Login Service | Sprint - 2
10 | Dev Accounts Page | Sprint - 3
11 | Test Accounts Page | Sprint - 3
12 | Test backup module | Sprint - 3
13 | Build reporting module | Sprint - 3
14 | Test reporting module | Sprint - 3
15 | Integration testing phase 1 | Sprint - 4
16 | Integration testing phase 2 | Sprint - 4 | Risks and Issues |  |  | Risks and Issues |  |  | Risks and Issues |  |  | Risks and Issues
17 | [5 empty] | 1. The team capacity needs to be looked at. 2, Some of the defects need re-design. 3. Login module took longer than expected.
18
19
20

## Data
Day | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Status
| Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | On Track
1 | 160 | 160 | 160 | 160 | 160 |  | 80 |  | Behind
2 | 144 | 150 | 144 | 150 | 144 |  | 72 |  | Delayed
3 | 128 | 140 | 128 | 140 | 128 |  | 64 |  | Complete
4 | 112 | 112 | 112 | 130 | 112 |  | 56
5 | 96 | 90 | 96 | 120 | 96 |  | 48
6 | 80 | 75 | 80 | 70 | 80 |  | 40
7 | 64 | 65 | 64 |  | 64 |  | 32
8 | 48 | 45 | 48 |  | 48 |  | 24
9 | 32 | 30 | 32 |  | 32 |  | 16
10 | 16 | 5 | 16 |  | 16 |  | 8
| 880 | 872 | 880 | 770 | 880 | 0 | 440 | 0