## Data
Budget used vs. sprint completion
Sprint (feature) | Planned Budget ($) | Spent Budget ($) | Budget Used (%) | Sprint completion (%) | Status
GUI | 1200 | 1050 | 87.5% | 90% | Good
Calendar Sync. | 700 | 720 | 102.9% | 100% | Bad
Message pop-up's | 500 | 420 | 84% | 75% | Bad
Invoice sent via E-mail | 900 | 420 | 46.67% | 100% | Good
Point retrieval | 350 | 280 | 80% | 50% | Bad
Overall | 3650 | 2890 | 79.18% | 88.49% | Good
Overall Remaining Days vs. Planned Days to Date | [5 empty] | Bugs to Fix vs. Resolved Bugs
Sprint (feature) | Planned Days | Spent Days | Status | Remaining Days |  | Sprint (feature) | Total Bugs | Resolved Bugs | Remaining Bugs
GUI | 20 | 14 | Good | 6 |  | GUI | 200 | 150 | 50
Calendar Sync. | 12 | 13 | Bad | -1 |  | Calendar Sync. | 792 | 792 | 0
Message pop-up's | 10 | 11 | Bad | -1 |  | Message pop-up's | 422 | 339 | 83
Invoice sent via E-mail | 8 | 6 | Good | 2 |  | Invoice sent via E-mail | 608 | 522 | 86
Point retrieval | 4 | 3 | Good | 1 |  | Point retrieval | 120 | 108 | 12
Overall | 54 | 47 | Good | 7 |  | Overall | 2142 | 1911 | 231
Overall Earned Value
Sprint (feature) | Earned ($) | Spent ($) | Cumulative Earned ($) | Cumulative Spent ($)
GUI | 1112 | 1050 | 1112 | 1050
Calendar Sync. | 689 | 720 | 1801 | 1770
Message pop-up's | 0 | 420 | 1801 | 2190
Invoice sent via E-mail | 589 | 420 | 2390 | 2610
Point retrieval | 302 | 280 | 2692 | 2890

## Risk Matrix
Risk | Likelihood | Impact | Place in Matrix | Mitigation | Cost of Mitigation ($) | --Impact-> | 5 | 5 | 10 | 15 | 20 | 25
We won't be grantd access to a certain DB | 5 | 2 | 10 | Pay for premium access | 1,200 per month |  | 4 | 4 | 8 | 12 | 16 | 20
the investors will pull their money | 1 | 5 | 5 | Reach out to variuos VC's for their investments | 500 |  | 3 | 3 | 6 | 9 | 12 | 15
[7 empty] | 2 | 2 | 4 | 6 | 8 | 10
[7 empty] | 1 | 1 | 2 | 3 | 4 | 5
[8 empty] | 1 | 2 | 3 | 4 | 5
----Likelihood--->
Column D is calculated according to the input in columns B and C